## Task Tracker
To-Do List |  |  | Total Tasks | 12 |  |  | 25%
|  |  | Completed | 3
Date: | 2025-11-24
[6 empty] | Cadre | 0
Complete | 0 |  | Top Two | #REF! |  | Urgent | 0
Working | 1 |  | COS | #REF! |  | High | 0
Started | 1 |  | OG | #REF! |  | Medium | 0
Not Started | 7 |  | CCE | #REF! |  | Low | 0
|  |  | S&E | #REF!
|  |  | IG | #REF!
CC | Task | Effort (hrs) | Status | Due Date | Days Left | Time Spent (hrs) | Notes
TRUE | Research Game Dev | 8 | Completed | 2025-10-26 | -29
TRUE | ABET Concerns | 6 | Completed | 2025-10-26 | -29
TRUE | Technical Specifications | 10 | Completed | 2025-11-09 | -15
FALSE | Game Flow Diagrams / State Design | 12 | Working | 2025-11-23 | -1
FALSE | UI Mockups + Architecture | 14 | Not Started | 2025-11-30 | 6 |  | Thanksgiving break push
FALSE | Core Architecture Build | 20 | Not Started | 2026-01-04 | 41 |  | Game loop, rule engine. Winter Break
FALSE | Data Structures & Unit Definitions | 8 | Started | 2026-01-25 | 62
FALSE | UI Prototype / Feedback | 10 | Not Started | 2026-02-22 | 90
FALSE | Multiplayer + Networking Implementation | 14 | Not Started | 2026-03-22 | 118
FALSE | Testing | 12 | Not Started | 2026-04-05 | 132
FALSE | Documentation | 8 | Not Started | 2026-04-12 | 139
FALSE | Showcase Prep | 8 | Not Started | 2026-04-19 | 146
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Formulas:
Days Left = IF(ISBLANK(Table1[[#This Row],[Due Date]]),"", Table1[[#This Row],[Due Date]]-TODAY())

## Sheet1
Task | Start Date | End Date | Milestone
Research AFWI mechanics | 2025-09-15 | 2025-10-01 | Research Complete
Research digital adaptations | 2025-09-20 | 2025-10-10 | Research Complete
Game flow diagrams & states | 2025-10-01 | 2025-10-20 | Game Design Documentation
Multiplayer framework research | 2025-10-15 | 2025-10-25 | Game Design Documentation
Software architecture planning | 2025-10-20 | 2025-11-10 | Game Design Documentation
Data structure design | 2025-11-01 | 2025-11-20 | Prototype UI/Data Structures
UI prototype | 2025-11-15 | 2025-12-10 | Prototype UI/Data Structures
Core game loop & rule engine | 2026-01-10 | 2026-02-15 | Multiplayer Implementation
Multiplayer/networking | 2026-02-01 | 2026-03-01 | Multiplayer Implementation
Testing mechanics & bug fixes | 2026-03-01 | 2026-04-01 | Testing & Documentation
Documentation (rules, tutorial) | 2026-03-15 | 2026-04-10 | Testing & Documentation
Final presentation prep | 2026-04-01 | 2026-04-15 | Senior Design Showcase

## Controls - Task Tracker
Complete | Category | Effort | Status
TRUE |  | Cadre | Not Started
FALSE |  | Urgent | Started
|  | High | Working
|  | Medium | Completed
Low